## CPM
Critical Path Method
HELP | [12 empty] | © 2010 Vertex42 LLC
| Start Date |  |  |  |  | Days to Completion
| 2010-01-11 08:00 |  |  |  |  | 73
Finish Date
2010-04-22
Times (in Days)
[6 empty] | Time Distribution: | Triangular | [5 empty] | [42] | [36 empty] | Series Used in the Gantt Chart | [7 empty] | Weeks | Days
ID | Task Name | Predecessors (Enter one ID per cell) |  |  | O (min) | M (most likely) | P (max) | Duration (exp. time) | ES | EF | LS | LF | Slack | EF of Predecessors | [9 empty] | Successors | [12 empty] | LS of Successors | [12 empty] | ES | Critical | +T | -T | Duration | +T | -T | Slack | Events | Events | Axis
10 | Start | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 | [5 empty] | 80 | [6 empty] | 0 | [5 empty] | 28 | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
20 | příprava všech ingrediencí | 10 |  |  | 8 | 8 | 8 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30 |  | 50 | 60 | 70 | [8 empty] | 13 |  | 28 | 8 | 31 | [6 empty] | 0 | 8 | 0 | 0 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 0.5
30 | zadělání těsta | 20 |  |  | 15 | 15 | 15 | 15 | 8 | 23 | 13 | 28 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 40 | [12 empty] | 28 | [9 empty] | 8 | #N/A | #N/A | #N/A | 15 | 0 | 0 | 5 | #N/A | #N/A | 1.5
40 | kynutí těsta | 30 |  |  | 0 | 0 | 0 | 0 | 23 | 23 | 28 | 28 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 90 | [12 empty] | 28 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.6 | 28 | 2.5
50 | příprava drobenky | 20 |  |  | 10 | 10 | 10 | 10 | 8 | 18 | 28 | 38 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 110 | [12 empty] | 38 |  |  | 8 | #N/A | #N/A | #N/A | 10 | 0 | 0 | 20 | #N/A | #N/A | 3.5
60 | zpracování ovoce | 20 |  |  | 30 | 30 | 30 | 30 | 8 | 38 | 8 | 38 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 110 | [12 empty] | 38 |  |  | 8 | 30 | 0 | 0 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 4.5
70 | vymazání plechu | 20 |  |  | 5 | 5 | 5 | 5 | 8 | 13 | 31 | 36 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 100 | [12 empty] | 36 |  |  |  | 8 | #N/A | #N/A | #N/A | 5 | 0 | 0 | 23 | #N/A | #N/A | 5.5
80 | vyhřátí trouby | 10 |  |  | 15 | 15 | 15 | 15 | 0 | 15 | 28 | 43 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 120 | [12 empty] | 43 |  | 0 | #N/A | #N/A | #N/A | 15 | 0 | 0 | 28 | #N/A | #N/A | 6.5
90 | vyválení těsta | 40 |  |  | 8 | 8 | 8 | 8 | 23 | 31 | 28 | 36 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 100 | [12 empty] | 36 |  |  |  | 23 | #N/A | #N/A | #N/A | 8 | 0 | 0 | 5 | #N/A | #N/A | 7.5
100 | přenesení těsta na plech | 70 | 90 |  | 2 | 2 | 2 | 2 | 31 | 33 | 36 | 38 | 5 | 13 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 110 | [12 empty] | 38 |  |  | 31 | #N/A | #N/A | #N/A | 2 | 0 | 0 | 5 | #N/A | #N/A | 8.5
110 | pokladení těsta švestkami a posypání drobenkou | 100 | 60 | 50 | 5 | 5 | 5 | 5 | 38 | 43 | 38 | 43 | 0 | 33 | 38 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 120 | [12 empty] | 43 |  | 38 | 5 | 0 | 0 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 9.5
120 | pečení | 110 | 80 |  | 30 | 30 | 30 | 30 | 43 | 73 | 43 | 73 | 0 | 43 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 130 | [12 empty] | 73 | 43 | 30 | 0 | 0 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 10.5
130 | Finish | 120 | [5 empty] | 0 | 73 | 73 | 73 | 73 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 14.6 | 73 | 11.5
[42]
Note on A9: Task ID: Normally, you would start by assigning IDs as 10, 20, 30, etc. However, the ID can be anything you want, including text.
Note on B5: Finish Date: The Finish Date uses the WORKDAY() function to calculate the date to completion, excluding weekends and the holidays listed in the Holidays worksheet. If you see a #NAME or other error in the Finish Date, you probably need to install the Analysis ToolPak and then recalculate the worksheet by pressing Ctrl+Alt+F9.
Note on B9: Task Name: The task name is a description that will show up in the gantt chart. The task name will be bolded if the task is a critical task. This is done through conditional formatting.
Note on C9: Predecessors: The set of events immediately preceding the task. In a network diagram or PERT chart, the predecessors for a particular task are all the tasks which have arrows pointing to that particular task. - Each predecessor needs to refer to the ID in column A. - If you need more than 6 predecessors, you can unhide columns I-L to increase the amount to 10. Successors: The set of events immediately following a particular task. In a network diagram or PERT chart, arrows are drawn from a task to its successors.
Note on M9: Optimistic Time (O): The minimum time required to complete the task. Assumes that everything proceeds faster than normal.
Note on N9: Most Likely Time (M): The most likely time required to complete the task, assuming everything proceeds as normal.
Note on O9: Pessimistic Time (P): The maximum time required to complete the task. Assumes that everything proceeds faster than normal.
Note on P9: Duration or Expected Time: Using a Beta distribution, where O is the minimum, P is the maximum, and M is the most likely value, the formula for calculating the mean or expected time is: Duration = (O+4M+P)/6 Using a Triangular distribution, the mean of the distribution would be: Duration = (O+M+P)/3
Note on Q9: Early Start Time: The ES is the maximum EF of all predecessors, except for the first task where the ES=0.
Note on R9: Early Finish Time: The EF time is the ES time plus the duration (EF=ES+Duration).
Note on S9: Late Start Time: The LS time is calculated as the LF time minus the duration (LS=LF-Duration).
Note on T9: Late Finish Time: The LF time is the minimum LS of all the successors, except for the last task where LF equals EF.
Note on U9: Slack Time: The Slack time is calculated as LF minus EF. It can also be calculated as LS minus ES. If the slack is zero, then the task is on the critical path.

## Holidays
Holidays to Exclude from Working Days
See help (F1) on the WORKDAY() function
Date | Non-Working Days
2009-01-01 | New Year's Day
2011-01-01
2009-12-25 | Christmas
2010-12-25
This worksheet lets you create a list of dates to be excluded from the number of Working Days. The WORKDAY() function already excludes weekends, so you only need to list dates for holidays and other non-working days. If your project spans more than one year, make sure you add dates for each year. The named range, holidays, is a dynamic named range ending at the last blank cell in column A. The comments column is just for your reference.

## TermsOfUse
Terms of Use
© 2011 Vertex42 LLC. All rights reserved.
This template is considered a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
Not for Resale or Public Sharing
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
Limited Private Sharing
Provided that you observe the above terms, you may share your edited version of this template *privately* with those specific people who **require** access to it within your immediate family, organization, or company.
* "Privately" means only accessible to those few people who you expressively give permission to view or edit your file. It is your responsibility to ensure that adequate security measures are used so that your file is not available to the public.
** Examples of acceptable private sharing with people who "require access" may include (a) sharing a budget spreadsheet with a spouse, (b) sharing a project schedule with your project team, or (c) sharing a timesheet with your employee or manager.
See the following page on Vertex42.com for the complete license agreement and examples of other allowed uses:
http://www.vertex42.com/licensing/EULA_privateuse.html
Disclaimer
This template is provided for informational or educational use only and is not intended to be relied on as medical, financial, legal, or other professional advice.
Vertex42 LLC makes no guarantee or representations about this template, or the accuracy or completeness of the content contained within this template.
Vertex42 LLC encourages you to seek the aid of a qualified professional before making decisions regarding health, financial, or legal issues.
Note on A3: No Warranties THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." VERTEX42, LLC MAKES NO WARRANTIES, EXPRESS OR IMPLIED, AND EXPRESSLY DISCLAIMS ALL REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Some states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.