## Slide 1: Metody sociálně geografického výzkumu Harmonogram aktivit bakalářské práce
7. Seminář
26.4. 2021
Veronika Kotýnková

## Slide 2: Zadání cvičení Harmonogram aktivit bakalářské práce
Zadání: Sestavte tabulku aktivit vedoucích k sepsání bakalářské práce včetně předpokládaného začátku, trvání i konce těchto aktivit. Jako termín odevzdání, ke kterému svůj harmonogram naplánujte, použijte 30. 4. 2023. Ideální časový krok harmonogramu použijte jeden semestr. Sestavte tak harmonogram pro 4 semestry (podzim 2021 – jaro 2023). Pro inspiraci můžete využít příkladu harmonogramu disertačního projektu či projektu základního výzkumu.
Doporučená forma odevzdání: tabulkový soubor
Doporučená délka: 1 tabulka (4 semestry x co nejpodrobnější aktivity)
Deadline: 2. 5. 2021 23:59

## Slide 3: Příklad harmonogramu aktivit 1
Tab. 1 Harmonogram projektu základního výzkumu
activity | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | responsibility
 | 1/4 | 2/4 | 3/4 | 4/4 | 1/4 | 2/4 | 3/4 | 4/4 | 1/4 | 2/4 | 3/4 | 4/4 | 
literature review updates | X | X |  |  |  |  |  |  |  |  |  |  | Porkertová
creating a contact database | X | X |  |  |  |  |  |  |  |  |  |  | Doboš
creating an interview structure | X | X |  |  |  |  |  |  |  |  |  |  | Pospíšilová
piloting the research interview |  | X |  |  |  |  |  |  |  |  |  |  | Osman
conducting interviews |  |  | X | X | X | X |  |  |  |  |  |  | Osman
conducting go-along research |  |  | X | X | X | X |  |  |  |  |  |  | Porkertová
transcription of interviews |  |  | X | X | X | X | X |  |  |  |  |  | Pospíšilová
writing the first article |  |  | X | X | X |  |  | 1 |  |  |  |  | Osman
data analysis |  |  |  |  | X | X | X | X | X | X |  |  | Doboš
writing the second article |  |  |  |  |  |  | X | X |  |  |  | 2 | Pospíšilová
writing the third article |  |  |  |  |  |  | X | X | X |  |  | 3 | Doboš
writing the fourth article |  |  |  |  |  |  |  | X | X | X |  | 4 | Porkertová
writing a fifth article |  |  |  |  |  |  |  | X | X | X |  | 5 | Osman
rewriting articles |  |  |  |  |  | X | X | X | X | X | X | X | Osman

## Slide 4: Příklad harmonogramu aktivit 2
Tab. 2 Harmonogram disertačního projektu
ongoing activity Time reserve | Time period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2019/2020 |  |  |  |  |  |  |  | 2020/2021 |  |  |  |  |  |  |  | 2021/2022 |  |  |  |  |  |  |  | 2022/2023 |  |  |  |  |  |  | 
Activity | 1. semestr |  |  |  | 2. semestr |  |  |  | 3. semestr |  |  |  | 4. semestr |  |  |  | 5. semestr |  |  |  | 6. semestr |  |  |  | 7. semestr |  |  |  | 8. semestr |  |  | 
Literature review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Main research question |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Data collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Analysing data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Interpreting data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Finalizing theoretical section of disertation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Finalising thesis - conclusion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Internship |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Advanced Master's State Examinations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First paper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Second paper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Third paper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Fourth paper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5: Otázky?
Děkuji za pozornost!